## Sheet1
Task | orig est | curr est | effort | remain | resposible
bilder runden | 1 | 0.18 | 0.18 | 0
select friend | 0.5 | 2 | 2 | 0
user to server to user | 3 | 3 | 3 | 0
0
statistik hinzufügen | 1.5 | 1.2 | 1.2 | 0
stats anzeigen | 0.25 | 0.2 | 0.2 | 0
change color | 0.5 | 2.5 | 2.5 | 0
remove friend | 0.75 | 1 | 1 | 0
datenbank aufsetzen | 7 | 5 | 5 | 0
0
user data speichern | 3 | 2.5 |  | 2.5
0
remove friend | 0.75 | 1.5 | 1.5 | 0
server comm. Database | 3 | 3.32 | 3.32 | 0
registrieren&log in | 3 | 5 | 5 | 0
create logo | 1 | 0.8 | 0.8 | 0
set default picture | 0.3 | 0.25 | 0.25 | 0
tb for each friend | 2 | 4 | 4 | 0
save changed user name | 1 | 1.5 | 1.5 | 0
generate info at right corner | 1.5 | 1.5 | 1.5 | 0
accept changed image pic | 0.5 | 1.75 | 1.75 | 0
friendship status | 3 | 2 | 2 | 0
socket to Gui | 3 | 9 | 9 | 0
Status/current activity | 1 | 2 | 2 | 0
hide messbox | 2 | 0.75 | 0.75 | 0
create Test Specification | 2 | 2 | 2 | 0
create Test Report | 0.5 | 0.5 | 0.5 | 0
making Testruns | 2 | 1.5 | 1.5 | 0
merch erverything (LOGIN/REGISTER/Database/MainWindow) | 3 | 2 | 2 | 0
Add friend with friendrequest | 1 | 4 | 4 | 0
safe/show stats per day | 5 | 5 | 5 | 0
bug fixes | 0.5 | 0.5 | 0.5 | 0
Release Documents | 8 | 8 | 8 | 0